## Work Breakdown Structure
Project(Name) |  |  |  |  | Resource Name
No | Task | Duration | Predecessor | Resource | NO | SIGN | Name | Resource Name
1 | Project planning and Management | 5 | Start | A,B,C | 1 | A | KHANT TI KYI | PROJECT MANAGER
2 | Requirement Analysis | 25 | 1 | A,B,D,F | 2 | B | MIN THU KHANT | BACKEND PROGRAMMER(SENIOR)
3 | Design | 20 | 1,2 | C,D,A, | 3 | C | AUNG PHONE KYAW | FRONTEND PROGRAMMER
4 | Coding | 30 | 1,2,3 | B,C,D,F | 4 | D | MYO THIHA TUN | DATABASE DEVELOPER
5 | Testing | 25 | 3,4 | E,D,F | 5 | E | SU PYAE THU YA | TESTER
6 | Debugging | 30 | 4,5 | A,B,C,E,F | 6 | F | YUN NANDI OO | BACKEND PROGRAMMER(JUNIOR)
7 | Customer Support | 10 | 6 | A,B,F
Project(Name)
1 | Project planning and Management
1.1 | Form Team
1.2 | Set Roles and Responsibilities
1.3 | Determine Project And Scope
1.4 | Determine Project Name And Team Name
1.5 | Determine Team Logo And Project Logo
2 | Requirement Analysis
2.1 | Gather Information
2.2 | Define System Repuirement
2.3 | Class Diagram
2.4 | Flow Chart
2.5 | ERD Diagram
2.6 | Use Case Diagram
3 | Design
3.1 | UX Design
3.2 | User Interface(UI)
3.3 | Design and integrate the network
3.4 | Design and integrate the database
4 | Coding
4.1 | Implement Database
4.2 | Implement GUI Design
4.3 | Implement Service-side functoins
4.4 | Implement client-side functions
5 | Testing
5.1 | BlackBox
5.2 | WhiteBox
5.3 | Client-side functions
5.4 | Service-side funcitons
5.5 | Security Testing
5.6 | User False
6 | Debugging
6.1 | Correcting code errors
6.2 | Remove bugs and errors
6.3 | Monitor project performance
6.4 | Maintenance and Modify functions
6.5 | Maintenance and Modify database
7 | Customer Support
7.1 | Documentation User Guide
7.2 | Documentation Technical Guide
7.3 | Training
7.4 | HardWare and Software Installing

## Network Diagram
| 0 | 5 | 5 | 5 | 25 | 30 | 30 | 20 | 50
Start |  | Task-1 |  |  | Task-2 |  |  | Task-3
| 0 | 0 | 5 | 5 | 0 | 30 | 30 | 0 | 50
[7 empty] | 50 | 30 | 80
Task-4
[7 empty] | 50 | 0 | 80
| 135 | 10 | 145 | 80 | 25 | 105 | 105 | 30 | 135
End |  | Task-7 |  |  | Task-6 |  |  | Task-5
| 135 | 0 | 145 | 80 | 0 | 105 | 105 | 0 | 135