## Sheet1
No | Bug Name | Date | Found by | Assigned To | Type | Priority | Description | Status
1 | QR code | 2018-12-25 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | QR code dose not show in UserInterface | Fixed
2 | Image | 2018-12-25 | MYO THIHA TUN | Aung Phone Kyaw | UI | 1 | Images of restaurant can't show at customer side | Fixed
3 | XML tag | 2018-12-25 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | writing code without XML tag | Fixed
4 | QR scan | 2018-12-27 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | when haven't coin and scanning QR code, exception appear | Fixed
5 | MAP (GPS) | 2018-12-27 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | After log in, and log in again without GPS access, exception appear | Fixed
6 | Password pop up | 2018-12-27 | MYO THIHA TUN | Aung Phone Kyaw | UI | 1 | Too many password box pop up appear | Fixed
7 | Rest logo | 2018-12-27 | MYO THIHA TUN | Aung Phone Kyaw | UI | 1 | When click rest logo, expception appear | Fixed
8 | Log in | 2018-12-27 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | When user cant complete login and then log in again cant login | Fixed
9 | Transaction Code | 2019-01-11 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | Transcation code not found at restaurant side | Fixed
10 | Gallery | 2019-01-11 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | Gallery not found at restaurant edit page | Fixed
11 | Stop Working | 2019-01-24 | MYO THIHA TUN | MIN THU KHANT | Code | 2 | App keep stop working at admin refund page | Fixed
12 | Restaurant home | 2019-01-24 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | Restaurant home without a proper login | Fixed
13 | API | 2019-01-24 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | Failure to connect to API | Fixed
14 | Admin Pie chart | 2019-01-24 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | Admin pie chart invalid parameter | Fixed
15 | variables 0 | 2019-01-24 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | if alll variables are 0 in admin pie chart | Fixed
16 | register restaurant | 2019-01-25 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | register restaurant without profile logo | Fixed
17 | update restaurant from home view | 2019-01-25 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | update restaurant profile logo from home view | Fixed
18 | restaruant Image | 2019-01-25 | MYO THIHA TUN | Aung Phone Kyaw | UI | 1 | Images can't found at restaruant side | Fixed
19 | API return | 2019-01-27 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | API return null of lat and long | Fixed
20 | Log in at restaurant | 2019-01-27 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | When click as restaurant , cant log in | Fixed
21 | Notification | 2019-01-27 | MYO THIHA TUN | Aung Phone Kyaw | Code | 1 | Can't show Noti when refund at Restaruant but working at admin noti page | Fixed
22 | Map | 2019-01-30 | MYO THIHA TUN | Aung Phone Kyaw | Code | 1 | cant show location at customer side | Fixed
23 | Restaurant QR page | 2019-01-30 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | Application restarting again and again at restaurant QR page | Fixed
24 | Key request modal | 2019-01-30 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | Key request modal not closing in Admin side | Fixed
25 | User profile view | 2019-01-31 | MYO THIHA TUN | MIN THU KHANT | Code | 1 | writing code without XML tag at customer side | Fixed